## Sheet1
Index | High Level Tasks | Responsibility | Status | Dependency | Planned End Date As per Old mpp | New Planned End Date | Actual End Date | Remarks | Attachment
1 | Migration of UAT environment - TCL UAT/DEV | PwC, SREI | Done |  | 2015-10-30 | 2016-02-15 | 2016-02-15 | Due to TCL Cloud issue, the entrire process was rolled back and performed again
2 | TCL PROD - VM Requirements to SREI | PwC | Done |  | 2016-04-13 | 2016-04-13 | 2016-04-13
3 | TCL PROD - VM allocation with access | SREI | Done | 2 | 2016-04-27 | 2016-04-27 | 2016-04-27
4 | TCL PROD - VM verification | PwC | For pending items fromSREI refer to remarks | 3 | 2016-04-27 | 2016-04-27 | 2016-04-27 | As per GAP Analysis report - 14th June 2016 the following : >> eBiz database nodes have missing mount points for Ambit file transfer >> eBiz Application Server and DB Node 1 less RAM >> SREI CDS database does not have ASM allocation
5 | TCL PROD - VM Gap Closing | SREI | Pending | 4 | 2016-04-30 | 2016-06-22 |  | As per GAP Analysis report - 14th June 2016 the following : >> eBiz database nodes have missing mount points for Ambit file transfer >> eBiz Application Server and DB Node 1 less RAM >> SREI CDS database does not have ASM allocation
6 | TCL PROD- VM Readiness Closure | PwC | Pending | 5 | 2016-04-30 | 2016-06-23
7 | TCL DR - VM requirements to SREI | PwC | Done |  | 2016-04-13 | 2016-04-17 | 2016-04-17 | Revised email from Caesar to Ritayan
8 | TCL DR - VM allocation with Access | SREI | Done and VPN access to TCL DR provided | 7 | 2016-04-27 | 2016-06-06 | 2016-06-06 | >> Email from Ritayan >> Till 08-Jun- No access though VMs are allocated
9 | TCL DR - VM verification | PwC | Done | 8 | 2016-06-14 | 2016-06-14 | 2016-06-14 | Email to SREI Discussed with Rakesh Shaw on missing RPMs etc on 16-Jun-16
10 | TCL DR - VM Gap Closing | SREI | Pending | 9 | 2016-06-15 | 2016-06-16
11 | TCL DR- VM Readiness Closure | PwC | Pending | 10 | 2016-06-16 | 2016-06-17
12 | Remote Desktop VPN access to PwC for On-premise SREI and Sahaj DC | SREI | Pending |  | 2016-06-16 | 2016-06-17 |  | >> VPN for SREI done >> VPN for SAHAJ pending - as discuused on 16th June it will be done by 17th
13 | Remote Desktop (2) allocation to PwC resources | SREI | Pending |  | 2016-06-16 | 2016-06-17 |  | >> Verbal reminder to SREI on 16th June >> Remote desktop access to SREI DC and SAHAJ DC
14 | N/w link between SREI DC and TCL PROD, N/w link between SREI DC and TCL DR, N/w link between TCL PROD and TCL DR | SREI | Pending |  | 2016-06-16 | 2016-06-17
15 | TCL Prod Preperation for SREI Orcle ebiz | PwC |  | 4,11,12 | 2016-06-25 | 2016-06-25 |  | RAC is ready
16 | TCL Prod Preperation for Sahaj Orcle ebiz | PwC |  | 4,11,12
17 | TCL Prod Preperation for SP01 | PwC |  | 4 | 2016-05-15 | 2016-05-15 | 2016-05-15
18 | TCL DR Preperation for SREI Orcle ebiz | PwC |  | 9,11,12 | 2016-06-29 | 2016-06-29
19 | TCL DR Preperation for Sahaj Orcle ebiz | PwC |  | 9,11,12 | 2016-06-29 | 2016-06-29
20 | TCL DR Preperation for SP01 | PwC |  | 9 | 2016-06-29 | 2016-06-29
21
22 | GMAIL, IMAP, and Sendmail configuration - TCL Prod environment | SREI |  |  | 2016-04-20 | 2016-07-01
23 | GMAIL, IMAP, and Sendmail configuration - TCL DR environment | SREI |  |  | 2016-04-20 | 2016-07-01
24 | SMS Gateway for alerts and Varpay application - TCL Prod environment | SREI |  |  | 2016-04-20 | 2016-07-01
25 | SMS Gateway for alerts and Varpay application - TCL DR environment | SREI |  |  | 2016-04-20 | 2016-07-01
26 | SREI Oracle eBiz Migration with DR | PwC |  | 6,11,12,13,14, 22, 23, 24, 25 | 2016-05-13 | 2016-07-09 |  | Requirements: >> All VM gaps related to Production and DR for eBiz to be closed >> VPN access for SREI DC >> N/w link between TCL PROD and TCL DR >> N/w link between SREI DC and TCL PROD >> Remote desktop access ** Delay in any one of the above will delay 09-Jul-16 ** SMS & Email alerts will be tested but not deployed
27 | SREI Oracle eBiz Migration - SREI UAT | SREI |  | 26 | 2016-05-18 | 2016-07-12 |  | Testing to be done in primary site only.
28 | SREI Oracle eBiz Migration - SREI UAT Issue Fix | PwC |  | 27 | NA | 2016-07-13
29 | SREI Oracle eBiz Migration - SREI UAT Sign Off | SREI |  | 28 | 2016-05-19 | 2016-07-14
30 | SREI Oracle eBiz Migration - Downtime | SREI |  | 29 | NA | 2016-07-15 |  | Early Morning by lunch time
31 | SREI Oracle eBiz Migration - Go Live Preparation activity | PwC |  | 30 | NA | 2016-07-18 |  | Before 11 AM
32 | SREI Oracle eBiz Migration - Go Live Release Communication | SREI |  | 31 | 2016-06-13 | 2016-07-18 |  | After 11 AM
33 | Sahaj Oracle eBiz Migration with DR | PwC |  | 6,11,12,13,14, 22, 23, 24, 25 | NA | 2016-07-09 |  | Requirements: >> All VM gaps related to Production and DR for eBiz to be closed >> VPN access for Sahaj DC >> N/w link between TCL PROD and TCL DR >> N/w link between SREI DC and TCL PROD >> Remote desktop access ** Delay in any one of the above will delay 09-Jul-16 ** SMS & Email alerts will be tested but not deployed
34 | Sahaj Oracle eBiz Migration - SREI UAT | SREI |  | 33 | NA | 2016-07-12 |  | Testing to be done in primary site only.
35 | Sahaj Oracle eBiz Migration - SREI UAT Issue Fix | PwC |  | 34 | NA | 2016-07-13
36 | Sahaj Oracle eBiz Migration - SREI UAT Sign Off | SREI |  | 35 | NA | 2016-07-14
37 | Sahaj Oracle eBiz Migration - Downtime | SREI |  | 36 | NA | 2016-07-15 |  | Early Morning by lunch time
38 | Sahaj Oracle eBiz Migration - Go Live Preparation activity | PwC |  | 37 | NA | 2016-07-18 |  | Before 11 AM
39 | Sahaj Oracle eBiz Migration - Go Live Release Communication | SREI |  | 38 | NA | 2016-07-18 |  | After 11 AM
40 | SP02 - Kastle Migration with DR | PwC |  | 6,11, 14,22,23,24,25 | 2016-05-11 | 2016-07-09 |  | Requirements: >> All VM gaps related to Production and DR for eBiz to be closed >> VPN access for SAHAJ DC >> N/w link between TCL PROD and TCL DR >> N/w link between SREI DC and TCL PROD >> Remote desktop access ** Delay in any one of the above will delay 09-Jul-16 ** SMS & Email alerts will be tested but not deployed
41 | Kastle application server installation and deployment at TCL Prod | SREI |  | 40 |  | 2016-07-09 |  | This will include connectivity with database
42 | Kastle application server installation and deployment at TCL DR | SREI |  | 40 |  | 2016-07-09 |  | This will include connectivity with database
43 | Kastle Application server - TCL prod to DR & Reverse connectivity | SREI |  | 40 |  | 2016-07-09
44 | SP02 - Kastle Migration - SREI UAT | SREI |  | 40 ::: 43 | 2016-05-19 | 2016-07-12 |  | Testing to be done in primary site only.
45 | SP02 - Kastle Migration - UAT Bug Fix | PwC |  | 44 |  | 2016-07-13
46 | SP02 - Kastle Migration - SREI UAT Sign off | SREI |  | 45 | 2016-05-19 | 2016-07-14
47 | SP02- Kastle Migration - Downtime | SREI |  | 46 |  | 2016-07-15 |  | Early Morning by lunch time
48 | SP02 - Kastle Migration - Go Live Preperation | PwC |  | 47 |  | 2016-07-18 |  | Before 11 AM
49 | SP02 - Kastle Migration - Go Live | SREI |  | 48 | 2016-06-13 | 2016-07-18 |  | After 11 AM
50 | Varpay application server installation & Deployment - TCL prod | PwC |  | 6 |  | 2016-08-01
51 | Varpay application server installation & Deployment - TCL DR | PwC |  | 11 |  | 2016-08-01
52 | Newgen Apache Load Balancer and JBOSS Installation - TCL Prod | PwC |  | 6 |  | 2016-08-01
53 | Newgen Apache Load Balancer and JBOSS Installation - TCL DR | PwC |  | 11 |  | 2016-08-01
54 | Ambit SIFL Application server installation & deployment - TCL Prod | SREI |  | 6 |  | 2016-08-01
55 | Ambit SIFL Application server installation & deployment - TCL DR | SREI |  | 11 |  | 2016-08-01
56 | Ambit SEFL Application server installation & deployment - TCL Prod | SREI |  | 6 |  | 2016-08-01
57 | Ambit SEFL Application server installation & deployment - TCL DR | SREI |  | 11 |  | 2016-08-01
58 | Paypro application server installation & deployment - TCL Prod | SREI |  | 6 |  | 2016-08-01
59 | Paypro application server installation & deployment - TCL DR | SREI |  | 11 |  | 2016-08-01
60 | SP01 (Ambit SEFL), SP02 (Ambit SIFL , Varpay, & Others), Newgen and SREI CDS Migration with DR | PwC |  | 6,11, 14,22,23,24,25 | 2016-06-30 | 2016-08-04 |  | Requirements: >> All VM gaps related to Production and DR to be closed >> N/w link between TCL PROD and TCL DR >> N/w link between SREI DC and TCL PROD >> Remote desktop access ** If ASM storage allocation is not provided for SREI CDS then local database would be created ** Delay in any one of the above will delay 09-Jul-16
61 | Deploy Ambit SEFL application - TCL Prod | SREI |  | 54, 60 |  | 2016-08-05
62 | Deploy Ambit SEFL application - TCL DR | SREI |  | 55,60 |  | 2016-08-05
63 | Deploy Ambit SIFL application - TCL Prod | SREI |  | 56,60 |  | 2016-08-05
64 | Deploy Ambit SIFL application - TCL DR | SREI |  | 57,60 |  | 2016-08-05
65 | Deploy Varpay application - TCL Prod | PwC |  | 50,60 |  | 2016-08-05
66 | Deploy Varpay application - TCL DR | PwC |  | 51,60 |  | 2016-08-05
67 | Deploy Newgen application - TCL Prod | SREI |  | 52,60 |  | 2016-08-05
68 | Deploy Newgen application - TCL DR | SREI |  | 53,60 |  | 2016-08-05
69 | Deploy Paypro application - TCL Prod | SREI |  | 58,50 |  | 2016-08-05
70 | Deploy Paypro application - TCL DR | SREI |  | 59,60 |  | 2016-08-05
71 | SP01 (Ambit SEFL), SP02 (Ambit SIFL , Varpay, & Others), Newgen and SREI CDS Migration with DR - SREI UAT | SREI |  | 60 ::: 70 | 2016-07-04 | 2016-08-10
72 | SP01 (Ambit SEFL), SP02 (Ambit SIFL , Varpay, & Others), Newgen and SREI CDS Migration with DR - SREI UAT Bug fixing | PwC |  | 71 |  | 2016-08-11
73 | SP01 (Ambit SEFL), SP02 (Ambit SIFL , Varpay, & Others), Newgen and SREI CDS Migration with DR - SREI UAT Sign off | SREI |  | 72 |  | 2016-08-12
74 | SP01 (Ambit SEFL), SP02 (Ambit SIFL , Varpay, & Others), Newgen and SREI CDS Migration with DR - Downtime | SREI |  | 73 |  | 2016-08-12 |  | Downtime by 1PM
75 | SP01 (Ambit SEFL), SP02 (Ambit SIFL , Varpay, & Others), Newgen and SREI CDS Migration with DR - Go Live Preparation | PwC |  | 74 |  | 2016-08-16
76 | SP01 (Ambit SEFL), SP02 (Ambit SIFL , Varpay, & Others), Newgen and SREI CDS Migration with DR - Go Live Communication | PwC |  | 75 | 2016-07-11 | 2016-08-16 |  | 14:00
77 | Database alert Configuration - TCL Prod | PwC |  | 6,11, 1422,23, 24, 25 |  | 2016-08-23
78 | Database alert Configuration - TCL DR | PwC |  | 6,11, 1422,23, 24, 25 |  | 2016-08-26
79 | RMAN backup configuration - TCL Prod | PwC |  | 6,11, 1422,23, 24, 25 |  | 2016-08-30