## Primary Site
DATED | 2016-06-09
Sl# | VM description | Host Name | IP Address | OS Version | Required mount points | External storage allocation | CPU cores | RAM | RPMs | IPs present | Required Ports present | Kernel Parameters | DNS name configured | Permissions | Graphic display and GUI installation | Ping to DR site | Remarks
1 | Oracle eBiz Application Server | DCPVAPPEBZ01 | 10.90.1.31 | OS version is 6.1 but not 5.11 | Mount point to window Ambit application server missing, /newdump | Yes allocated as per requirement | 16 CPU OK | 15.6 GB instead of 26GB | OK | All present | All Ports OK | All kernel parameters as desired OK | OK | Permissions OK | OK | OK
2 | Oracle eBiz Database Node 1 | DCPVORAEBZ01 | 10.90.1.32 | OS version is 6.1 but not 5.11 | Mount point to window Ambit application server missing | Yes allocated as per requirement | 14 CPU OK | 11GB instead of 26GB | OK | All present | All Ports OK | All kernel parameters as desired OK | OK | Permissions OK | OK | OK
3 | Oracle eBiz Database Node 2 | DCPVORAEBZ02 | 10.90.1.33 | OS version is 6.1 but not 5.11 | Mount point to window Ambit application server missing | Yes allocated as per requirement | 10 CPU Ok | 26GB OK | OK | All present | All Ports OK | All kernel parameters as desired OK | OK | Permissions OK | OK | OK
4 | Ambit SEFL Database Node 1 | DCPVORAABT01 | 10.90.1.25 | OS version is 6.1 but not 5.11 | OK | Missing as required is 403GB instead of 332GB | 8 CPU OK | 18 GB OK | OK | All present | All Ports OK | All kernel parameters as desired OK | OK | Permissions OK | OK | OK
5 | Ambit SEFL Database Node 2 | DCPVORAABT02 | 10.90.1.26 | OS version is 6.1 but not 5.11 | OK |  | 8 CPU OK | 18 GB OK | OK | All present | All Ports OK | All kernel parameters as desired OK | OK | Permissions OK | OK | OK
6 | AMBIT SIFL,KASTLE,VARPAY Database Node 1 | DCPVORAABT03 | 10.90.1.27 | OS version is 6.1 but not 5.11 | OK | Missing as required is 200GB instead of 160GB | 4 CPU OK | 8.7 GB OK | OK | All present | All Ports OK | All kernel parameters as desired OK | OK | Permissions OK | OK | OK
7 | AMBIT SIFL,KASTLE,VARPAY Database Node 2 | DCPVORAABT04 | 10.90.1.28 | OS version is 6.1 but not 5.11 | OK |  | 4 CPU OK | 8.7 GB OK | OK | All present | All Ports OK | All kernel parameters as desired OK | OK | Permissions OK | OK | OK
8 | NEWGEN Database Node 1 | DCPVORANGN03 | 10.90.1.29 | OS version is 6.1 but not 5.11 | OK | Missing as required is 260GB instead of 225GB | 4 CPU OK | 12 GB OK | OK | All present | All Ports OK | All kernel parameters as desired OK | OK | Permissions OK | OK | OK
9 | NEWGEN Database Node 2 | DCPVORANGN04 | 10.90.1.30 | OS version is 6.1 but not 5.11 | OK |  | 4 CPU OK | 12 GB OK | OK | All present | All Ports OK | All kernel parameters as desired OK | OK | Permissions OK | OK | OK
10 | SREICDS Database Single Node | DCPVORANDB01 | 10.90.1.34 | OS version is 6.1 but not 5.11 | Missing /newdump | Missing as required is 75GB | 4 CPU OK | 8 GB OK | OK | All present | All Ports OK | net.ipv4.conf.default.rp_filter = 2 ;fs.aio-max-nr = 1048576 ;fs.file-max = 6815744 ;kernel.sem = 250 32000 100 128; net.ipv4.ip_local_port_range = 9000 ; net.core.rmem_max = 419430465500; net.core.rmem_default = 262144; net.core.wmem_default = 262144; net.core.wmem_max = 1048586 | OK | Permissions OK | OK | OK | We cannot proceed to installation till the ASM storage is allocated
11 | RMAN repository Node | DCPVORARMN02 | 10.90.1.35 | OS version is 6.1 but not 5.11 | Yes alocated | Yes allocated as per requirement | 2 CPU OK | 4 GB OK | OK | All present | All Ports OK | All kernel parameters as desired OK | OK | Permissions OK | OK | OK
sreiadmin/We1c0me@123

## DR Site
Sl# | VM description | Host Name | IP Address | OS Version | Required mount points | External storage allocation | CPU cores | RAM | RPMs | IPs present | Required Ports present | Kernel Parameters | DNS name configured | Permissions | Graphic display and GUI installation | Ping to Primary Site | LUN/Raw Devices | Remarks
1 |  | DRPVORAABT03 | 10.90.1.201 | 6.1 | found | not found | 6 | 10GB | ok | yes | all | yes | no | not checked | x11 | no | not informed | Please Recheck
2 |  | DRPVAPPEBZ01 | 10.90.1.202 | 6.1 | found | not found | 6 | 10GB | ok | yes | all | yes | no | not checked | x11 | no | not informed | Please Recheck
3 |  | DRPVORAEBZ01 | 10.90.1.202 | 6.1 | found | not found | 8 | 16GB | ok | yes | all | yes | no | not checked | x11 | no | not informed | Please Recheck
4 |  | DRPVORANDB01 | 10.90.1.203 | 6.1 | found | not found | 8 | 16GB | ok | yes | all | yes | no | not checked | x11 | no | not informed | Please Recheck
5 |  | DRPVORAABT01 | 10.90.1.204 | 6.1 | found | not found | 6 | 10GB | ok | yes | all | yes | no | not checked | x11 | no | not informed | Please Recheck
6 |  | DRPVORANGN03 | 10.90.1.205 | 6.1 | found | not found | 8 | 14GB | ok | yes | all | yes | no | not checked | x11 | no | not informed | Please Recheck
6 |  | DRPVORANGN03 | 10.90.1.206 | 6.1 | found | not found | 10 | 16GB | ok | yes | all | yes | no | not checked | x11 | no | not informed | Please Recheck
LUN details are not provided
Connectivity
|  |  |  | DR | TO | Promises | No
|  |  |  | Promises | TO | DR | No | Through VPN only
|  |  |  | DR | TO | DC | No
|  |  |  | DC | TO | DR | Yes

## MISSING_RPM
VM description | Host Name | IP Address | Possible Missing RPMs
| DRPVORAABT03 | 10.90.1.201 | na
| DRPVORAEBZ01 | 10.90.1.202 | na
| DRPVORANDB01 | 10.90.1.203 | na
| DRPVORAABT01 | 10.90.1.204 | na
| DRPVORANGN03 | 10.90.1.205 | na
| DRPVORANGN03 | 10.90.1.206 | na

## Primary_To_Standby_MAP_Details
Sl# | VM description | DC Host Name | DC IP | DR Host Name | DR IP
1 | SP02 | DCPVORAABT03 | 10.90.1.27 | DRPVORAABT03 | 10.90.1.201
|  | DCPVORAABT04 | 10.90.1.28
2 | Ebiz App | DCPVAPPEBZ01 | 10.90.1.31 | DRPVAPPEBZ01 | 10.90.1.202
3 | Ebiz DB | DCPVORAEBZ01 | 10.90.1.32 | DRPVORAEBZ01 | 10.90.1.203
|  | DCPVORAEBZ02 | 10.90.1.33
4 | SREI CDS | DCPVORANDB01 | 10.90.1.34 | DRPVORANDB01 | 10.90.1.204
5 | SP01 | DCPVORAABT01 | 10.90.1.25 | DRPVORAABT01 | 10.90.1.205
|  | DCPVORAABT02 | 10.90.1.26
6 | NGP01 | DCPVORANGN03 | 10.90.1.29 | DRPVORANGN03 | 10.90.1.206
|  | DCPVORANGN04 | 10.90.1.30